## Guideline
GUIDELINE OF RISK MANAGEMENT
1. Purpose
To guide all FSOFT departments/projects for Risk Management
2. Scope
Application to all FSOFT departments/projects
3. Definition & Criteria
Risks are those events or conditions that may occur, and if it does take place, has a
harmful or negative effect on a project
Risk Factor Chart is used as starting point for identifying risks for projects. It contains 1. TOP commonly occurring risks at software projects executed at Fsoft. This list has been compiled from Post-mortem report of previous projects 2. Risk Source and Risk Categories
Risk Sources are the fundamental drivers that cause risks within a project or organization. There are many sources of risks, both internal and external to a project. Risk sources identify common areas where risks may originate
Risk Categories reflect the “bins” for collecting and organizing risks. A reason for identifying risk categories is to help in the future consolidation of the activities in the risk mitigation plans
Risk Assessment Matrix is a template used to record the result of Risk Management activities
Probability - How likely is this risk to occur?
Impact - How bad will it be if it happens?:
Risk Exposure is a simple calculation that gives a numeric value to a risk, enabling different risks to be compared in order to setting risk priority. Risk Exposure of any given risk = Probability of risk occurring x total loss/impact if risk occurs
Trigger determines how to know if the risk occur so you’ll know when and if put contingency action in place.
Mitigation actions are the actions taken BEFORE those risks occur to reduce the probability and/or the impact of risks
Contingency actions are the actions taken AS those risks do occur to reduce their impact
4. Procedure for Risk Management
a- Risk assessment:
|  | a-1 | Identify Risk: A Project manager use a list of commonly occurring risks in Risk Factor Chart and Process asset to get information about risk and risk management on similar projects. Evaluating and thinking about previously encountered risks also help identifying other risks that may be pertinent to this project but do not appear on the list. Project managers can also use their judgment and experience to evaluate the situation to identify potential risks. Another alternative is to use the project kick-off meetings to elicit views on risks from others.
|  | a-2 | Analyze Risk: You estimate the probability of its occurrence and its impact when it does occur. The product of these values is called Risk Exposure. If Probability is the probability of a risk occurring and if Impact is the total loss incurred if the risk materializes
*Estimate Probability of risk: Determine if the likelihood of it actually occurring is High, Medium or Low, then figure Probability on a scale from 0.0 to 1.0 as 1.0 is the highest
|  |  | Probability | Explanation
|  |  | High (0.8 - 1.0) | Exhibits the high risk cue, has happened frequently, has a very significant chance of happening in the future
|  |  | Medium (0.4 - 0.7) | Has happened occasionally or has a reasonable but not completely expected chance of happening in the future
|  |  | Low (0.0 - 0.3) | Has happened very infrequently or is expected not to happen * Note: if the probability of the risk occurring is ZERO, then it will be removed from consideration, so its status is changed to CLOSED
*Estimate Impact of risk: Figure Impact on a scale from 0.0 to 10.0 as follows:
|  |  | Project Objective | Scope | Quality | Cost | Time
|  |  | High (8.0 - 10.0) | >20% project size affected | Quality reduction unacceptable to sponsor OR Quality performance reduce >20% Target | >20% project effort/cost increase | >20% project duration increase
|  |  | Moderate (4.0 - 7.0) | 11%-20% project size affected | Quality reduction requires sponsor approval OR Quality performance reduce 11% - 20% Target | 11%-20% project effort/cost increase | 11%-20% project duration increase
|  |  | Low (0.0 - 3.0) | <=10% project size affected OR Minor areas of project scope affected | Quality performance reduce <=10% Target | <10% project effort /cost increase | <=10% project duration increase
*Prioritize Risk: Firstly, calculate Risk Exposure by the following equation: Risk Exposure = Probability x Impact Then, Risk Priority is identified according to the rule below:
[5 empty] | Exposure | Priority
[5 empty] | 7.1 - 10.0 | High
[5 empty] | 4.0 - 7.0 | Medium
[5 empty] | 0.1 - 3.9 | Low
The risks that have the highest Exposure should be given the highest priority for corrective action, for example, a high-probability, high-impact risk will have higher priority than a risk with a medium probability and high impact. In case of conflict, use your judgment.
b- Risk control:
|  | b-1 | Develop Risk Response Plan: Once the risks have been prioritized, you must decide Risk handling strategy and mitigation plan to identify what to do about them. Which ones will be managed is a management decision. Perhaps only the top few need to be handled in a project. Risk handling options includes:
|  |  | Risk handling strategy | Action |  |  | Criteria
|  |  | Manage | Mitigation & Contingency actions are required to be identified and implemented to reduce probability and/or the impact of risks to an acceptable threshold. Taking early action to reduce the probability and/or impact of a risk is often more effective than trying to repair the damage after the risk has occurred. |  |  | Risk Priority is High and Medium
|  |  | Avoid | Risk avoidance involves changing the project management plan to eliminate the threat posed by risks, to isolate project objectives from the risk's impact, or to relax the objective that is in jeopardy, such as extending the schedule or reducing the scope. Some risks that arise early in the project can be avoided by clarifying requirements, obtaining information, improving communication, or acquiring expertise
|  |  | Transfer | Risk transfer requires shifting the negative impact of the risk, along with the ownership of the response, to the third party. Transferring the risk simply gives another party responsibility for its management, it does not eliminate the risk. Risk transference nearly always involve payment of a risk premium to the party taking the risk. Transference tool include, but are not limited to, the use of insurance, performance bonds, warranties, guarantees, etc.
|  |  | Accept | No plan to deal with the risk The project can live with the consequences if the risk actually occur |  |  | Risk Priority is Low OR Unable to identify another suitable strategy
*Plan Mitigation actions needed to to reduce the probability and/or the impact of risks before those risks occur by refer Risk factor chart to a list of commonly used risk mitigation action for various risk and select a suitable one. You can use also Process Asset to identify the risk and mitigation actions. Cost-benefit analysis of risk mitigation options is required for High Risk of projects ranked A.
*Plan Contingency actions to reduce the impact if a risk does occur. Again, it is just mandatory to develop contingencies for High and Medium Risk.
Those actions must be executed and monitored. To ensure that the needed actions are executed properly, you must updated the project schedule to include the defined mitigation actions.
|  | b-2 | Monitor risks: Monitor and revaluate the risks periodically at milestones or event-driven, to see - Status of risks with active mitigating strategies, updating of risk parameters and decision on changing to the alternative option. - Evaluate the triggers for risks with approaching due date in order to decide when and if you should activate the risk contingency plan - Assessing the project status to identify new risks The results of this review are reported in Risk Assessment matrix as a part of each milestone report, you report the status of the risk mitigation action along with the current risk perception and strategy. To prepare this report, you make a fresh risk analysis to determine whether the priorities have changed. At the end of projects, report of Risk management activities is prepared as part of Project postmorterm report. It will be integrated into the organizational process asset for subsequent projects usage.

## Risk Assessment Matrix
RISK ASSESSMENT MATRIX
Risk ID | Risk Source | Risk Category | Risk Description | Probability | Impact | Exposure | Priority | Trigger | Risk Status | Last updated date | Mitigation | Contigency | Person in charge | Planned end date | Mitigation Cost | Mitigation Benefit | Actual end date | Action Status | Customer | Business Processes Complexity
R01 | Project Requirement | Not meeting performance requirements | Quality of document which is wrote by Japanese maybe not good | 0.3 | 2 | 0.6 | 4 | Member don’t know more Japanese. | Open |  | 1.Create plan to training Japanese for member from beginning of project. |  | Team member | [5 empty] | Human resource | Critical Dependencies | Open
[11 empty] | 2. Using English instead of Japanese (if can). |  | Team member | [5 empty] | Project Characteristics | Data Migration Required | In-progress
[11 empty] | 3.When deliver documents to customer can write by two languages: English and Japanese. |  | Team member | [5 empty] | Project Dependencies | Design Difficulty | Passed
R02 | Human resource | Shortage of Human resource | Member leave team while running project. | 0.2 | 8 | 1.6 | 3 | Member being absent at the meeting minues and cannot contact | Open |  |  | If risk occurs, PM assigns work to other member. | Team member | [5 empty] | Project Environment | Existing System Documentation | Pending
[19 empty] | Project Management | External driven decisions forced on the project | Cancelled
[19 empty] | Project Requirement | Hardware Constraints
R03 | Project Management | Insufficient PM Experience | PM may not follow the process because lacks of project management skill. | 0.5 | 5 | 2.5 | 1 | Project is not follow the process | Open |  | 1.PM ask for helping from Supervisor when need. |  | HuyenPT | [5 empty] | Technical | Implementation Difficulty
[11 empty] | 2.PM self-study about Project Management Skill |  | HuyenPT | [6 empty] | Inexperience Customer/End User
Inexperience with Project Process
R04 | Technical | Process risk | Delivery report day is delay. | 0.6 | 4 | 2.4 | 2 | Schedule is unclearly and member don't know about delevery report day | Open |  | PM must make schedule clearly and take care specially to delivery day. |  | Team member | [6 empty] | Inexperience with Project Technology
R05 | Project Requirement | Not meeting performance requirements | Change requirement | 0.4 | 6 | 2.4 | 2 | Requirement is changed when designing/ coding or testing | Open |  | Change design, code, test case |  | Team member | [6 empty] | Insufficient PM Experience
R06 | Project Management | Structure risk | Not suitable schedule | 0.5 | 6 | 3 | 3 | Schedule is not suitable, duration is too long or too short | Open |  | Change schedule |  | Team member | [6 empty] | Insufficient business knowledge
R07 | Project Requirement | Not meeting performance requirements | Miss requirement | 0.4 | 7 | 2.8 | 2 | The product of project cannot meet fully requirements | Open |  | PM must make schedule clearly and take care specially to delivery day. |  | Team member | [6 empty] | Integration Complexity
R08 | Human resource | Shortage of Human resource | Developer of project doesn't have any experience about .Net language and unit test for .Net | 0.3 | 6 | 1.8 | 4 | Developer has not worked or studied with .Net language before. | Open |  | - Have plan for developer to study and code demo by .Net language before the project start. - Refer unit test of Fsoft's project. |  | Team member | [6 empty] | Lack of Customer Support
R10 | Human resource | Shortage of Human resource | During the time doing project, member of project may have problem and can't do their job fully. | 0.6 | 9 | 5.4 | 5 | - Their job may be late and affect project schedule. | Open |  | - Always have the people to support for another when it is necessary |  | Team member | [6 empty] | New Technology
R11 |  | Human resource | Conflict among team members | 0.5 | 7 | 3.5 | 5 | - Has issue inside the team | Open |  | - Plan some teambuilding to improve teammate |  | Team member
Parralell development
Physical Facilities
Project Complexity
Risky Dependencies
Shortage of Human resource
Team Spirit and Attitude
Test Ability
Too many requirement changes
Tools Availability
Unclear Acceptance Criteria
Unclear Acceptance criteria and process
Unclear Decision Making Process
Unclear requirements
Unrealistic schedules
Unstable Customer Organization
Vendor/External Support
Weak Customer Involvement
Note on C3: Get info from Risk factor chart
Note on E3: How likely is this risk to occur Low: 0.0-0.3 Medium: 0.4-0.7 High: 0.8-1.0 1.0 is the highest
Note on F3: How bad will it be if it happens Low: 0-3,0 Medium: 4,0-7,0 High: 8,0-10,0 10 is the highest
Note on G3: If >0.5, Mitigation & Contigency plan to be prepared to managed this risk if <=0,3,mitigation actions are not required, but the contigency plan
Note on H3: Rank from 1 to 10, 1 is the highest priority. The higher risk exposure is, the higher risk priority is
Note on I3: determine how to know if the risk occur so you’ll know when and if put contingencies in place. Do this for High and Medium risks (Risk exposure is 0.0-10)
Note on K3: The date this risk is latest updated
Note on L3: If >0.5, Mitigation & Contigency plan to be prepared to managed this risk if <=0,3,mitigation actions are not required, but the contigency plan Enter row to add more mitigation as necessary
Note on M3: If >0.5, Mitigation & Contigency plan to be prepared to managed this risk if <=0,3,mitigation actions are not required, but the contigency plan Enter row to add more contigency action as necessary
Note on N3: Person in charge of mitigation/Contigency
Note on O3: If status of this risk is Open, enter Planned end date of Mitigation If status of this risk is Closed, enter Planned end date of Contigency
Note on Q3: Use this column to evaluate benefit of mitigation action. 1. If risk does not occur mitigation benefit is calculated based on estimated impact and mitigation cost. 2. if risk occurred mitigation benefit is calculated based on the decrease of actual loss and handling cost (estimated impact-mitigation cost-contingency cost)
Note on R3: If status of this risk is Open, enter Actual end date of Mitigation If status of this risk is Closed, enter Actual end date of Contigency
Note on L4: Consider threshold (estimated impact is over Fsoft norm and profanity is high)-->we have plan handling options and based on constrains with customer and project to select the best one.

## Risk Factor Chart
RISK FACTOR CHART
ID | Risk Category | Risk Source | Mitigation Action | Process | Top 10 Risk | Probability
[6 empty] | Development | Maintenance | Test | Call center | ERP Implementation | Migration/ Conversion
1 | Project Dependencies | Critical Dependencies: items on which project is dependent are subject to personnel, decision-making, or component shortfalls. Or the items could not be available when needed or incompatible with parts of approach, no clear plan or schedule for how the whole system will come together. | 1. Remind customer in advance through weekly report, email, TV meeting, chatting, Tele conference 2. Buffer sufficient effort and time to verify customer supplied product before usage, 3. Buffer effort and schedule for the delay and bugs | Project management | 1 | x | x | x | x | x | x
2 | Human Resource | Inexperienced with Project Process | 1, Make estimates with a buffer for initial learning time 2, Maintain buffers of extra resources 3, Define a project-specific training program 4, Conduct cross-training sections | Project management | 2 | x | x | x | x | x | x
3 | Human Resource | Inexperienced with Project Technology | 1, Make estimates with a buffer for initial learning time 2, Maintain buffers of extra resources 3, Define a project-specific training program 4, Conduct cross-training sections | Project management | 2 | x | x | x |  | x | x
4 | Human Resource | Insufficient business knowledge, no availability of experts in that business domain | 1, Increase interaction with the client and ensure adequate knowledge transfer. 2, Organize domain knowledge training. 3, Simulate or prototype the business transaction for the client and get it approved. | Project management | 2 | x | x | x | x | x | x
5 | Project Requirement | Unclear requirements: requirements incomplete or unclear, or some requirements only in the head of the customer | 1, Use experience and logic to make some assumptions and keep the client informed; obtain sign-off 2, Develop a prototype and have the requirements reviewed by the client. | Requirement | 3 | x | x | x |  |  | x
6 | Customer | Unclear Acceptance Criteria have not been explicitly addressed or in dispute between project team and customer | 1, Use experience and logic to make some assumptions and keep the client informed; obtain sign-off 2, Develop a prototype and have the requirements reviewed by the client. | Requirement | 3 | x | x | x |  | x | x
7 | Project Requirement | Too many requirement changes: rapidly changing or no agreed-upon baseline | 1, Obtain sign-off for the initial requirements specification from the customer. 2, Convince the customer that changes in requirements will affect the schedule 3, Define a procedure to handle requirement changes 4, Negotiate payment on actual effort | Requirement | 4 | x | x | x |  | x | x
8 | Project Characteristics | Unrealistic schedules: date is fixed by need to meet marketing demo, trade show, legal mandate, financial goal, or similar driver independent of project team estimate of time needed to do the work | 1, Negotiate for a better schedule. 2, Identify parallel tasks. 3, Have resources ready early 4, Identify areas that can be automated 5, If the critical path is not within the schedule, negotiate with the client 6, Negotiate payment on actual effort. | Contract management | 5 | x | x | x |  | x | x
9 | Technical | New Technology | 1, Consider a phased delivery 2, Begin with the delivery of critical modules 3, Include time in the schedule for a learning curve. 4, Provide training in the new technology. 5, Develop a proof-of-concept application. | Coding | 6 | x | x | x |  | x | x
10 | Human Resource | Team Spirit and Attitude: little or no commitment to the project; not a cohesive team | 1, Ensure that multiple resources are assigned on key project areas. 2, Have team-building sessions. 3, Rotate jobs among team members 4, Keep extra resources in the project as backup. 5, Maintain proper documentation of each individual's work. 6, Follow the configuration management process and guidelines strictly. | Project management | 7 | x | x | x | x | x | x
11 | Project Infrastructure | Physical Facilities: Major modifications needed, or facilities nonexistent | 1. Make estimates with a buffer effort and time to verify customer supplied product before usage 2. Maintain buffer resource and schedule for the delay and bugs | Configuration management | 8 | x | x | x | x | x | x
12 | Project Infrastructure | Tools Availability: non-validated, proprietary or major development needed; no documentation | 1. Make estimates with a buffer effort and time to verify customer supplied product before usage 2. Maintain buffer resource and schedule for the delay and bugs | Configuration management | 8 | x | x | x | x | x | x
13 | Technical | Not meeting performance requirements | 1, Define the performance criteria clearly and have them reviewed by the client. 2, Define standards to be followed to meet the performance criteria 3, Prepare the design to meet performance criteria and review it. 4, Simulate or prototype performance of critical transactions. 5, Test with a representative volume of data where possible. 6, Conduct stress tests where possible. |  | 9 | x | x |  |  | x | x
14 | Project Management | External driven decisions forced on the project | 1, Outline disadvantages with supporting facts and data and negotiate with the personnel responsible for forcing the decisions 2, If inevitable, identify the actual risk and follow its mitigation plan | Requirement | 10 | x | x | x | x | x | x
15 | Technical | Link failure or slow performance | 1, Set proper expectations with the client 2, Plan ahead for the link load 3, Plan for optimal link usage. | Design/Coding |  | x | x |  |  | x | x
16 | Customer | Unstable Customer Organization: management or organization structure is continually or rapidly changing |  | Contract management |  | x | x |  | x | x | x
17 | Customer | Lack of Customer Support: little or no support. No visible support; no help on unresolved issues |  | Contract management |  | x | x |  | x | x | x
18 | Customer | Unclear Decision Making Process by an amorphous group of managers, with no designated leader or process |  | Contract management |  | x | x |  | x | x | x
19 | Customer | Weak Customer Involvement: minimal or no user involvement; little user input |  | Contract management |  | x | x |  |  | x | x
20 | Customer | Inexperience Customer/End User: no previous experience with similar projects; unsure of how needs can be met |  | Contract management |  | x | x |  | x | x | x
21 | Customer | Unclear Acceptance criteria and process: process is not in place for user approvals and users do not accept any concepts or design details of system |  | Contract management |  | x | x |  |  | x | x
22 | Project Requirement | Business Processes Complexity: business processes vary considerably among the users |  | Requirement |  |  |  |  | x | x | x
23 | Project Characteristics | Project Complexity: large, highly complex, or not decomposable |  | Project management |  | x | x |  |  | x | x
24 | Project Infrastructure | Hardware Constraints: significant hardware-imposed constraints; multiple platforms |  | Requirement |  | x | x |  |  |  | x
25 | Technical | Test Ability: Inability to verify/validate products against requirements | abvc | Test |  | x | x |  |  | x | x
26 | Technical | Design Difficulty: unclear how to design, or interfaces not well defined or controlled; subject to change |  | Design |  | x | x |  |  |  | x
27 | Technical | Implementation Difficulty: algorithms and/or design have components this team will find difficult to implement |  | Design/Coding |  | x | x |  |  | x | x
28 | Project Dependencies | Existing System Documentation: no documentation exists for current systems or existing documentation is out of date and incorrect |  | Project management |  | x | x | x | x | x | x
29 | Project Dependencies | Parallel development: interface software/system/platform under development along with the project's software |  | Configuration management |  | x | x | x | x | x | x
30 | Project Management | Insufficient PM Experience: PM has no experience with this type of project or is new to project management |  | Project management |  | x | x |  |  | x | x
31 | Project Characteristics | Data Migration Required: much data to migrate; several types of databases or no good descriptions of what is where |  | Configuration management | [5 empty] | x | x
32 | Technical | Integration Complexity: extensive interface with external hardware/software required |  | Design/coding |  | x | x |  |  | x | x
33 | Human Resource | Shortage of Human resource: high turnover, not available for a role that is key to this project |  | Project management |  | x | x | x | x | x | x
34 | Project Dependencies | Vendor/External Support: little or no support, high cost, and/or poor response time |  | Requirement |  | x | x |  |  |  | x